Wendens Ambo Neighbourhood Plan Steering Group

Meeting 13: 3 December 2025, 5 - 6.15pm, virtual meeting

Minutes and Actions

Attendees: Cliff Snow, Anita Chandraker, Alistair Forbes, Ann Wade, Liz Johnson, Richard Walford

Apologies: Alan Lovett, Kathryn Butterworth

- Item 1: Minutes of the previous meeting were approved. All due actions have been completed. AC also noted that Brian Cole has stepped down from the Neighbourhood Plan Steering Group and the Parish Council. He has been thanked for his support

- Item 2: AC informed the team that monthly updates of progress and budget have been provided to the Parish Council. Feedback on progress has been positive from Parish Councillors and District Councillors and they remain supportive of the need for a plan. The request for funding for the next financial year is still to be considered and approved.

- Item 3: AC explained that the SG were asked by the Parish Council to review the Newport, Quendon and Rickling Neighbourhood Plan that was issued for Reg 14 consultation and propose a response to be sent from the Parish Council. This has been completed and submitted and acknowledgement received.

- Item 4:  CS provided an update on the Character Assessment. Working in teams of two, the Steering Group has completed and submitted the assessment form templates to CS and he has uploaded these for review by Ian Poole. CS is now reviewing the photographs taken to support the Character Assessment and will upload these in due course

- Item 5: CS has consolidated the completed Organisation Survey responses. The group noted that there are a range of suggestions/needs which should be shared with the Parish Council for consideration but which do not fall within the core scope of the Neighbourhood plan eg communal storage for equipment, expansion of cricket facilities and more pitches, promotion of Neighbourhood Watch.

- Item 6: Regular updates continue to be provided to the community via Village Views. Potential timing for the next event for the village was discussed. The purpose should be to share all inputs gathered to date, including the Character Assessment

- AOB:

  - RW informed the group that the new Estate Manager for Audley End Estate is keen to meet members of the team. It was agreed that a meeting should be organised as soon as possible

  - AC shared that Nicky Joshua from RCCE had been in touch. She has capacity to support us as we develop the plan

  - AC requested that one or two people attend the next Parish Council meeting in her absence on 5 January and provide an update on progress.

  - CS will add the recent Village Views articles to the websites It was agreed that once completed, the Character Assessments should be widely circulated for comment.

  - Next meeting will be 28 January 2026 at 7pm

Actions

Carried forward actions

  - Amended to: CS/RW to consider formulating a mutually supportive policy through discussion with Newport Neighbourhood Plan team regarding the land between Salmon Field and Rookery Lane and also the possibility of agreeing a boundary change between the two parishes. Continue to review

Actions from Meeting 13

13.1 CS to review and pass on photographs to Ian Poole to support the Character Assessment

13.2 As the NP is developed, extract and include the suggestions and requests made through the Organisation Surveys. CS to share responses with Ian Poole.

13.3 Share availability to attend a meeting with Audley End Estates with RW (All)

13.4 One or two members of the SG to attend the Parish Council meeting on 5 Jan.